## 050-G-DAT-50001-001-RB-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | REFINERY TANK FARM
2 | Text Box | 1 | MAK | General Comments: - Use the latest datasheet template that is part of the Homogenization Procedure. - Always use the long description of Unit names unless the space doesn't permit. - The correct equipment tag nos. shall be used. Refer to the latest Equipment List (Item Index).
3 | Text Box | 2 | A Albalooshi | The information provided for the driver starting method of the pumps is not applicable (Closed/Open – valve (unloaded) start)), It shall be corrected as DOL or VFD starting method as per detail design. Please provide the basis/ philosophy of providing this requirement on the driver starting method. A general note shall be added as follows "Motors shall be designed to suite the driver online starting method as per BMPS-P19 clause 5.4 and BMPS-P18 clause 5.4.". The (Closed/Open – valve (unloaded) start)) shall be moved in the relevant field in the data sheet.
4 | Cloud+ | 2 | MAK | 050 - REFINERY TANK FARM
5 | Cloud+ | 7 | MAK | 050P0955/0956
6 | Cloud+ | 7 | MAK | Don't used FEED doc nos.
7 | Cloud+ | 7 | MAK | 050P0955/0956
8 | Cloud+ | 7 | MAK | Use correct tag no. 050P0530
9 | Cloud+ | 7 | MAK | 050P0955/0956
10 | Cloud+ | 7 | MAK | 050P3278
11 | Cloud+ | 7 | MAK | 050P0955/0956
12 | Cloud+ | 8 | MAK | 050P0955
13 | Cloud+ | 8 | MAK | 050P0955
14 | Cloud+ | 8 | MAK | 050P0956
15 | Cloud+ | 8 | MAK | 050P5030
16 | Cloud+ | 9 | MAK | 050P0956
17 | Cloud+ | 9 | MAK | 050P5030
18 | Cloud+ | 9 | MAK | 050P0955
19 | Cloud+ | 9 | MAK | 050P0956
20 | Cloud+ | 10 | MAK | 050P0956
21 | Cloud+ | 10 | MAK | 050P0955
22 | Cloud+ | 11 | MAK | 050P0955
23 | Cloud+ | 11 | MAK | 050P0956
24 | Cloud+ | 12 | MAK | 050P0956
25 | Cloud+ | 12 | MAK | 050P0955
26 | Cloud+ | 13 | MAK | 050P0955
27 | Cloud+ | 13 | MAK | 050P0956