## 050-G-DAT-50002-001-RB-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comments: - Use the latest datasheet template that is part of the Homogenization Procedure. - Always use the long description of Unit names unless the space doesn't permit. - The correct equipment tag nos. shall be used. Refer to the latest Equipment List (Item Index).
2 | Cloud+ | 1 | MAK | REFINERY TANK FARM
3 | Cloud+ | 2 | MAK | 050 - REFINERY TANK FARM
4 | Text Box | 2 | A Albalooshi | The information provided for the driver starting method of the pumps is not applicable (Closed/Open – valve (unloaded) start)), It shall be corrected as DOL or VFD starting method as per detail design. Please provide the basis/ philosophy of providing this requirement on the driver starting method. A general note shall be added as follows "Motors shall be designed to suite the driver online starting method as per BMPS-P19 clause 5.4 and BMPS-P18 clause 5.4.". The (Closed/Open – valve (unloaded) start)) shall be moved in the relevant field in the data sheet.
5 | Call-out | 2 | MAK | Delete space
6 | Call-out | 3 | MAK | Delete space
7 | Text Box | 4 | AliRedha Malalla | Where Applicable; please correct to SOCKET
8 | Call-out | 4 | MAK | Delete space
9 | Call-out | 5 | MAK | Delete space
10 | Call-out | 6 | MAK | Delete space
11 | Cloud+ | 7 | MAK | 050P5038A/B
12 | Call-out | 7 | MAK | Delete space
13 | Cloud+ | 7 | MAK | 934P1001A/B
14 | Cloud+ | 7 | MAK | 050P5033A/B/C
15 | Cloud+ | 7 | MAK | 050P5038A/B
16 | Cloud+ | 7 | MAK | 010P0001A/B
17 | Cloud+ | 7 | MAK | 050P5033A/B/C
18 | Cloud+ | 7 | MAK | 934P1001A/B
19 | Cloud+ | 7 | MAK | 010P0001A/B
20 | Call-out | 7 | MAK | Delete space