## 050-G-DAT-50003-001-RB-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | Delete space
2 | Text Box | 1 | MAK | General Comments: - Use the latest datasheet template that is part of the Homogenization Procedure. - Always use the long description of Unit names unless the space doesn't permit. - The correct equipment tag nos. shall be used. Refer to the latest Equipment List (Item Index).
3 | Call-out | 1 | MAK | Delete space
4 | Cloud+ | 1 | MAK | REFINERY TANK FARM
5 | Text Box | 2 | A Albalooshi | The information provided for the driver starting method of the pumps is not applicable (Closed/Open – valve (unloaded) start)), It shall be corrected as DOL or VFD starting method as per detail design. Please provide the basis/ philosophy of providing this requirement on the driver starting method. A general note shall be added as follows "Motors shall be designed to suite the driver online starting method as per BMPS-P19 clause 5.4 and BMPS-P18 clause 5.4.". The (Closed/Open – valve (unloaded) start)) shall be moved in the relevant field in the data sheet.
6 | Cloud+ | 2 | MAK | 050 - REFINERY TANK FARM
7 | Call-out | 2 | MAK | Delete space
8 | Call-out | 2 | MAK | Delete space
9 | Call-out | 2 | Mohamed Aldoseri | Classification shall be confirmed after the hazardous area classification drawing, consider using API 500 for exisiting area as stated in BMPS-P2, clause 3,C.
10 | Call-out | 3 | MAK | Delete space
11 | Call-out | 3 | MAK | Delete space
12 | Call-out | 4 | MAK | Delete space
13 | Call-out | 5 | MAK | Delete space
14 | Call-out | 6 | MAK | Delete space
15 | Cloud+ | 7 | MAK | 050P5033A/B/C
16 | Cloud+ | 7 | MAK | 010P0001A/B
17 | Cloud+ | 7 | MAK | 934P1001A/B
18 | Cloud+ | 7 | MAK | 050P5038A/B
19 | Call-out | 7 | MAK | Delete space
20 | Cloud+ | 8 | MAK | 050P5033A/B/C
21 | Cloud+ | 8 | MAK | 050P5038A/B
22 | Cloud+ | 8 | MAK | 934P1001A/B
23 | Text Box | 8 | AliRedha Malalla | OEM design shall ensure dry steam inlet to seal quench.
24 | Cloud+ | 8 | MAK | 010P0001A/B
25 | Call-out | 8 | MAK | Delete space