## 050-G-DAT-50004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 2 | Mohamed Aldoseri | Discrepancy with P1011 data sheet attached. Confirm area classification.
3 | Call-out | 2 | Mohamed Aldoseri | q
4 | Call-out | 3 | Abdul Rahim | Pls confirm
5 | Text Box | 4 | Isamu | All seal flush and seal barrier liquid lines shall be piping as per FEED data sheet. Correct and apply. Process side mech seal flushing also require flush plan. Please check with pump/seal maker and correct accordingly.
6 | Text Box | 5 | Isamu | All inspection and test specified as witnessed on FEED data sheet shall remain witnessed. The use of the term Observed in the data sheet is rejected. Correct accordingly and put a remark as agreed on the definitions of words between API / BMPS and ITP
7 | Text Box | 5 | Ahmed Bucheeri | YES
8 | Text Box | 5 | Ahmed Bucheeri | YES
9 | Call-out | 7 | MAK | Critical Comment: Full equipment nos. shall be entered, e.g. 050P1011. Apply this change in all documents and drawings.