## 050-G-DAT-50005-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | Delete space
2 | Text Box | 1 | MAK | General Comments: - Use the latest datasheet template that is part of the Homogenization Procedure. - Always use the long description of Unit names unless the space doesn't permit. - The correct equipment tag nos. shall be used. Refer to the latest Equipment List (Item Index).
3 | Cloud+ | 1 | MAK | Use adequate title
4 | Call-out | 2 | Mohamed Aldoseri | Area classification shall be confirmed after the final HAC drawing, considering API 500 as indicated in BMPS-P2- Typical to all pumps/motors in existing areas.
5 | Call-out | 2 | Mohamed Aldoseri | Correct the information
6 | Typewritten Text | 2 | Nabeel | Hydraulics of injecting into the Main Diesel transfer line #540 to Sitra should be confirmed by EPC
7 | Callout | 2 | A Albalooshi | This pump shall be located under a roof.
8 | Text Box | 2 | Mohamed Aldoseri | X