## 050-G-DAT-55001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Ahmed Ali | use the latest pumps number
2 | Text Box | 1 | MAK | This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template shall be used.
3 | Call-out | 2 | Abdulaziz | Summer peak time temperature shall be considered.
4 | Callout | 2 | Abdul Rahim | looks low, confirm
5 | Call-out | 2 | Mahdi Ali | Shall be 1RHCU without spaces.
6 | Text Box | 2 | Abdulaziz | API 610 edition shall be indicated
7 | Text Box | 2 | Abdulaziz | Bearing housing & bearings shall be designed for oil mist lubrication in compliance to BMPS G8
8 | Callout | 2 | alexis.martinez | Page 2, rows 33/34. Inconsistency of maximum ambient temperature and relative humidity shown in page 2 and page 7. Review and correct
9 | Cloud+ | 2 | Mohamed Ayyash | Cooling water is the stream name and not the source. Need to specify the plant where it is coming from.
10 | Callout | 2 | alexis.martinez | Suction vacuum pressure is not allowed. Review booster pump system to resolve this issue.
11 | Callout | 3 | Berik.Nurbolatov | Should be updated for the next revision: Case, impeller,shaft data; bearings type;.
12 | Call-out | 3 | Abdulaziz | Oil ISO VG Grade 68 shall be considered as an option.
13 | Text Box | 3 | Abdulaziz | Bearing housing & bearings shall be designed for oil mist lubrication in compliance to BMPS G8
14 | Callout | 3 | Berik.Nurbolatov | Nozzle data should be added.
15 | Text Box | 3 | Abdulaziz | Pump DBSE shall be greater than the cartridge seal length to facilitate insitu seal repair
16 | Callout | 4 | Berik.Nurbolatov | Please advise the cooling required data.
17 | Call-out | 4 | Abdulaziz | Bearings temperature monitoring shall be considered.
18 | Call-out | 5 | Abdulaziz | All observed tests shall be changed to WIT.
19 | Callout | 5 | Erwin.Lugue | Equivalent weight in S.I. units to be provided
20 | Text Box | 5 | Abdulaziz | Yes
21 | Call-out | 6 | Abdulaziz | Typo
22 | Callout | 7 | Sankara | ON LINE
23 | Text Box | 7 | Abdulaziz | Accelerometer Required for motor Acc BMPS-A3 Parag.8.5
24 | Callout | 9 | Abdul Rahim | confirm
25 | Call-out | 9 | Abdulaziz | Minimum flow shall be reviewed
26 | Text Box | 9 | Abdulaziz | M/SEAL vendor shall be provided with operating parameter during, start-up/shutdown mode, study state condition an upset in order to provide the optimum design selection.
27 | Cloud+ | 9 | Ahmed.Marhoon | A clarification required from Contractor for deleting technical notes from Datasheet. One of the notes was regarding requirement of instrumentation scope which has been excluded in the new revision. Also, the system to capture requirements for the instrumentation and control scope on relevant RFI documents, to be discussed and agreed with the Contractor.
28 | Call-out | 9 | Abdulaziz | Skin thermocouple shall be provided to avoid rapid heating up that might damage the seals. BMPS G2 para 6.1.35