## 050-G-DAT-55002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ali Kadhem | As part of value improvement, please assess the flushing oil requirement for the BMP units, the 3HDU operating senarios and steam balance and check the requirement of 2 Steam Turbine driven/1 Electric Motor driven. Please provide technical justification of the current arrangement of 2 Steam Turbine driven/1 Electric Motor driven.
2 | Call-out | 1 | Hasan Al Noaimi | BOOSTER
3 | Callout | 1 | Mohamed Ayyash | Change in all pages
4 | Text Box | 1 | alexis.martinez | GENERAL: All Equipment Numbers need to be updated as per the new numbering provided by owner. This applies to all sheets
5 | Call-out | 1 | Abdulaziz | Pumps tag no to be indicated
6 | Text Box | 1 | Mahdi Ali | The Driver equipment tag shall change accordingly
7 | Text Box | 1 | A.Jabbar Mahmood | The owner has not recieved the hydrualic calculations and hence cannot verify the pumps head, suction and discharge operating and design conditions.
8 | Text Box | 1 | Sameer Foujdar | The right tag numbers for the pumps are 021P0013A/B/C and the driver tag numbers are 021T0013A/B and 021M0013C. To be changed in the entire document.
9 | Text Box | 1 | MAK | Use the latest document cover page and API datasheet template which is part of the Homogenization Procedure. MOC Contractor shall coordinate with JV Directorate.
10 | Text Box | 2 | CK Samy | 100%
11 | Text Box | 2 | CK Samy | 113
12 | Cloud+ | 2 | Mohamed Ayyash | Align
13 | Text Box | 2 | Abdulaziz | API 610 edition to be indicated
14 | Cloud+ | 2 | Mohamed Ayyash | Avoid overlap with table lines.
15 | Text Box | 2 | Abdulaziz | Bearing housing & bearings shall be designed for oil mist lubrication in compliance to BMPS G8.
16 | Call-out | 2 | Hasan Al Noaimi | BOOSTER
17 | Text Box | 2 | Mahdi Ali | Change Material Class to 'G' instead of 'K'
18 | Callout | 2 | Yousif Ahmadi | Change: REFINERY TANK FARM
19 | Cloud+ | 2 | Mohamed Ayyash | Cooling water is the stream name and not the source. Need to specify the plant where it is coming from.
20 | Cloud+ | 2 | A.Jabbar Mahmood | Design capacity shall be reviewed and confirmed considering all the possible operating senarios, as explained in the Bapco MoM submitted (Refer to owner email dated 17-May-2018. from Raj to TR)
21 | Callout | 2 | alexis.martinez | Page 2, Operating Conditions Section. Include the missing values which were included on FEED Data Sheet.
22 | Callout | 2 | alexis.martinez | Page 2, row 19. The suction pressure is higher than FEED datasheet. The reference used in both cases should be the same because the suction is from existing tanks. Review, correct and explain as required.
23 | Callout | 2 | alexis.martinez | Page 2, row 32, 33. Inconsistency of max. ambient temperature and relative humidity shown in page 2 and 7. Review and correct
24 | Call-out | 2 | Edgardo | Please clarify why steam data is N/A; Note that two of the drivers are turbine
25 | Text Box | 2 | Mahdi Ali | Remove the letter 'f'
26 | Cloud+ | 2 | Mohamed Ayyash | Typo. Change to THREE
27 | Cloud+ | 2 | Mohamed Ayyash | Use 2/8 (as in page one). Apply to all pages.
28 | Call-out | 3 | Abdulaziz | Bearing housing & bearings shall be designed for oil mist lubrication in compliance to BMPS G8.
29 | Call-out | 3 | Abdulaziz | Grouted baseplate is recommended as per API 610 para. 7.3.8 & 7.3.20
30 | Call-out | 3 | Abdulaziz | Shrink fit impellers is not recommend from maintenance prospective .
31 | Call-out | 3 | Abdulaziz | Supplier to consider oil mist viscosity grade ISO VG 68 which is subjected to plant equipment types, configuration and operating condition
32 | Call-out | 3 | Abdulaziz | To clarify the basis for selecting Hydraulic fit coupling
33 | Callout | 4 | Adnan Alothman | Seal supp. sys. mounted on Pump Baseplate to be checked and confirm against relative standard.
34 | Cloud+ | 5 | Mohamed Ayyash | Avoid overlap, continue on the next line.
35 | Cloud+ | 5 | Mohamed Ayyash | Avoid overlap, continue on the next line.
36 | Text Box | 6 | Ahmed Marhoon | The following are general comments related to instrumentation and control: 1. The notes related to Instrumentation & Control provided on the Data Sheet do not capture all the technical requirements for the instruments design. In the RFI, all applicable BMPS-J series to be referenced (such as J2, J3 …etc) for the supplier to comply with. 2. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification that will be sent out to suppliers. In case this document would be the only one for MR, then all the relevant BMPS to be included in the Data Sheet notes. 3. Vendors to be notified on the fact that the final design of the system shall include all the Hazop3/SIL recommendations and approved PID post-EPC-development. 4. Since the Data Sheet is issued separately, the consistency between the different documents, that may be part of the requisition, could not be verified and hence it is the contractor’s responsibility to update the other documents impacted by any of the comments on this Data Sheet and vice versa. 5. Minimum Flow arrangement/design shall be reviewed and confirmed by the supplier. The minimum flow configuration shall be designed taking into consideration all the operating requirements i.e. number of pumps in operation at the same time. Preference is to have individual minimum flow lines to ensure proper sizing of valves and provide adequate/practical protection system for the pumps. 6. Supplier to be notified on consideration of the Start Permissive (linked MOVs status) requirements per the PID. 7. Add Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. 8. Requirement of MCM to be verified with the supplier. Reference to BMPS-J15 MCM to be added accordingly. 9. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 10. If applicable, all the BN machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 11. Narrative/flow charts/cause and effect shall be provided in client’s standard format for any control or sequence logic. 12. Assistance and involvement of the vendor during CHAZOP/Hazop workshops and study to be considered. 13. Explanatory notes to be added on the requirement of having the control performed in the plant DCS and safety functions in ESD system. 14. Scope of supply for the interposing relays to be clearly defined. 15. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 16. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 17. Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval.
37 | Callout | 7 | alexis.martinez | Page 7, row 3. Check ambient temperature based on BMPS-A1 and BMPS-A3.
38 | Call-out | 7 | Edgardo | Please update the tag number and unit number
39 | Call-out | 7 | CK Samy | Required if motor rating greater than75kW
40 | Cloud+ | 7 | Mohamed Ayyash | This is site location not unit names. Need to mention units names.
41 | Text Box | 8 | A.Jabbar Mahmood | Currently a common minimum spillback line is provided for the three pumps. Since these pumps can serve different units at the same time, TR shall review the requirement of individual spillback lines for each pump. TR shall also design the spillback lines with sufficient length to ensure enough heat dissipation and avoid pump overheating. In some operating senarios, any of these pump could operate at very low flowrates for extended time. A note may need to be included in this D/S in this regard.
42 | Call-out | 8 | Abdulaziz | For parallel operation, proper hydraulic study with stable head flow curves pump selection shall be considered in addition to system design to cater for flow induced vibration.
43 | Text Box | 8 | Mahdi Ali | Incorrect format for equipment number
44 | Call-out | 8 | A.Jabbar Mahmood | It is suggested that TR include the possible operating scenarios for pump vendor reference.
45 | Call-out | 8 | Abdulaziz | M/Seal vendor to be aware of such concern to design and select the best option.
46 | Text Box | 8 | Abdulaziz | M/SEAL vendor to be provided with operating parameter during, start-up/shutdown mode, study state condition an upset in order to provide the optimum design selection.
47 | Call-out | 8 | A.Jabbar Mahmood | Typo "1RHCU"
48 | Call-out | 8 | Abdulaziz | Variable drive motor could be selected as an alternative option.