## 050-G-DAT-55003-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Raj | General: Use the correct equipment tag for unit 934.
2 | Text Box | 1 | Ahmed.Marhoon | JV replies on comments related to instrumentation and control scope in previous revision need to be discussed with the concerned personnel at the MOC for mutual agreement on way forward.
3 | Call-out | 1 | Raj | Use correct unit no. 934
4 | Cloud+ | 1 | Mohamed Ayyash | Unit name is missing from all pages
5 | Text Box | 1 | MAK | General Comment: This datasheet template was revised and will be issued with the Homogenization Procedure. In the next revision, the revised template and cover page shall be used.
6 | Cloud+ | 2 | A.Jabbar Mahmood | Commented earlier, based on Bapco's experience temperature can drop below 180 F. Please note that 2HCU cold feed temp from storage is specified as 150F. Most of the heat loss is in storage tank. For pump design, it is believed that it is more conservative to consider lower temps that correspond to higher fluid density and viscosity.
7 | Callout | 2 | alexis.martinez | Page 2. The pump is operating in vacuum conditions. Review
8 | Callout | 2 | Mohamed Ayyash | Delete u085 and write "TOWER"
9 | Callout | 2 | Fernando.Perez | which component create corrosion Quantity to be provided in related space
10 | Callout | 2 | Fernando.Perez | Group shall be only one
11 | Call-out | 2 | Mahdi Ali | Material class for turbine shall follow the pump. Change material class 'K' to 'G'
12 | Callout | 3 | Fernando.Perez | Flanged & Valved Acc BMPS-G2
13 | Callout | 3 | Fernando.Perez | Check material as corrosion due to ?????
14 | Callout | 3 | Fernando.Perez | Coupling Guard to be included
15 | Callout | 5 | Fernando.Perez | Acc Feed Data Sheet shall be Witnessed
16 | Cloud+ | 7 | Mohamed Ayyash | This is project site location not unit. Need to write name of unit.
17 | Callout | 7 | Fernando.Perez | Group shall be only one
18 | Call-out | 8 | A.Jabbar Mahmood | As commented earlier: Shall read as "SR HVGO for 2HCU start-up (for about one week post start-up)"