## 050-G-DAT-55004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Fernando.Perez | Include Unit #, Doc.Code
2 | Text Box | 1 | MAK | Use the latest document cover page and API datasheet template which is part of the Homogenization Procedure. MOC Contractor shall coordinate with JV Directorate.
3 | Call-out | 2 | Abdulaziz | API 610 edition to be indicated
4 | Cloud+ | 2 | Mohamed Ayyash | Avoid overlap with table lines.
5 | Cloud+ | 2 | Mohamed Ayyash | Cooling water is the stream name and not the source. Need to specify the plant where it is coming from.
6 | Callout | 2 | alexis.martinez | Discharge and suction pressure at rated conditions are not matching with FEED data sheet. Review and correct as it needs
7 | Cloud+ | 2 | Mohamed Ayyash | enlarge font in line with other in same column
8 | Callout | 2 | alexis.martinez | Page 2, row 32, 33. Inconsistency of max. ambient temperature and relative humidity shown in page 2 and 7. Review and correct
9 | Text Box | 2 | Mahdi Ali | Remove letter 'f'
10 | Callout | 2 | Fernando.Perez | Should be Group II
11 | Callout | 2 | Yousif Ahmadi | Site: REFINERY TANK FARM
12 | Callout | 2 | Fernando.Perez | Specify if In Line (OH) or Suspended (VS)
13 | Text Box | 2 | Abdulaziz | These are crucial parameters to be provide for pump designer , selection of material and M/seal type.
14 | Call-out | 2 | Abdulaziz | Vendor to consider minimum flow spill back in order to prevent flow recirculation, overheating and flow induced vibration.
15 | Call-out | 2 | Abdulaziz | Vertical electric motors shall be frame size 180 and larger (3 hp [2.24 kW]) with ball bearings that have re greasable construction or that are designed for oil mist service. Motor bearing housing shall be provided with provision for oil mist supply and drain at upper and lower part of the bearings
16 | Call-out | 3 | Abdulaziz | Pump and motor shall be mounted on a rigid foundation to provide sufficient structural stiffness, absorb the energy generated and damp the vibration. Therefore, its supplier & contractor responsibility to review the design of the foundation and provide the optimum design subjected to owner approval. Reference API 610 parg 7.3.20
17 | Call-out | 3 | Abdulaziz | Supplier to consider oil mist viscosity grade ISO VG 68 which is subjected to plant equipment types, configuration and operating condition.
18 | Text Box | 4 | Isamu | Plan 13 is for volatile high vapor pressure saturated liquids and not suitable for this application. Consult with Vendor for alternative.
19 | Cloud+ | 5 | Mohamed Ayyash | ???
20 | Cloud+ | 5 | Mohamed Ayyash | Align, use justify from the left
21 | Cloud+ | 5 | Mohamed Ayyash | Avoid overlap, continue on the next line.
22 | Cloud+ | 5 | Mohamed Ayyash | Avoid overlap, continue on the next line.
23 | Cloud+ | 5 | Yousif Ahmadi | Should be Witness per FEED data sheet
24 | Call-out | 6 | Abdulaziz | Pump suction strainer to be considers
25 | Text Box | 8 | Mahdi Ali | Incorrect motor number. Motor Sequence number shall follow the Pump number. This tag shall be 010M0031A/B
26 | Call-out | 8 | CK Samy | Motors shall be provided a. local bearing temperature indicators. b. 2 (two) Pt100 RTD, three wire type, in each bearing
27 | Text Box | 8 | Mahdi Ali | Remove letter'f'
28 | Call-out | 9 | Abdulaziz | Oil ISO VG Grade 46 / 68.
29 | Call-out | 9 | CK Samy | required for 2MW and above
30 | Text Box | 10 | Abdulaziz | Pump shall be protected against dry run to ensure problem free operation.
31 | Call-out | 10 | Sameer Foujdar | As per the PFD no 050-A-PFD-50001-008 slop oil injection and Bahrain/Rubble crude injection locations to be checked and confirmed.
32 | Call-out | 10 | Abdulaziz | Back flush connection shall be provided if sea C/W in use.
33 | Call-out | 10 | 986131 | correct the location of mixture as per the PFD's
34 | Text Box | 10 | Mahdi Ali | Incorrect Equipment numbers
35 | Call-out | 10 | Hasan Al Noaimi | Number changed to 010P0031A/B
36 | Call-out | 10 | Abdulaziz | Typo error: NPSH r shall be at least 4ft less than NPSH a
37 | Text Box | 11 | Ahmed Marhoon | The following are general comments related to instrumentation and control: 1. The notes related to Instrumentation & Control provided on the Data Sheet do not capture all the technical requirements for the instruments design. In RFI, all applicable BMPS-J series to be referenced (such as J2, J3 …etc) for the supplier to comply with. 2. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification that will be sent out to suppliers. 3. Vendors to be notified on the fact that the final design of the system shall include all the Hazop3/SIL recommendations and approved PID post-EPC-development. 4. Since the Data Sheet is issued separately, the consistency between the different documents, that may be part of the requisition, could not be verified and hence it is the contractor’s responsibility to update the other documents impacted by any of the comments on this Data Sheet and vice versa. 5. Minimum Flow arrangement/design shall be reviewed and confirmed by the supplier. 6. Supplier to be notified on consideration of the Auto-Start (linked to discharge pressure) and Permissive signals as captured on the respective PID sheet (sequence and interlocks shall be finalized during detail design in consultation with vendor). 7. Add Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. 8. Requirement of MCM to be verified with the supplier. Reference to BMPS-J15 MCM to be added accordingly. 9. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 10. All the BN machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 11. Narrative/flow charts/cause and effect shall be provided in client’s standard format for any control or sequence logic. 12. Assistance and involvement of the vendor during CHAZOP/Hazop workshops and study to be considered. 13. Explanatory notes to be added on the requirement of having the control performed in the plant DCS and emergency safety functions in ESD system. 14. Scope of supply for the interposing relays to be clearly defined. 15. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 16. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 17. Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval.