## 050-G-DAT-55004-001-RB-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Fernando.Perez | As agreed change it by: CENTRIFUGAL PUMP DATA SHEET
2 | Call-out | 1 | Mahdi Ali | Unit number for those pumps shall be finalized. Tag numbers shall be changed accordingly.
3 | Callout | 1 | Abdul Rahim | change to corresponding unit
4 | Text Box | 1 | Isamu | Delete "Mechanical". This is IFI and not for your internal drafting
5 | Callout | 2 | Abdul Rahim | confirm physical properties for crude oil
6 | Callout | 2 | Fernando.Perez | Check Group should be one
7 | Text Box | 2 | Isamu | Delete "Mechanical".
8 | Call-out | 2 | 986131 | H2S is present in crude, use conservative estimate considering the AB crude MSDS.
9 | Call-out | 2 | 986131 | not clear why suction pressure is negative - please submit system hydraulics for our review. Pump is vertical type below grade level as per the schematic
10 | Call-out | 2 | 986131 | the volumetric flow is exactly equal to the PFD BPD figure which is at standard condition. Please review if the actual flow rate needs to be changed based on the the temperature.
11 | Call-out | 2 | 986131 | both chloride and water is present in the crude. Use salt and water for unsettled crude. Please raise a technical query to TPIT to obtain the water in crude to be used based on the tank design philosophy (including dewatering arrangement) and also post BMP the crude would be supplied by a newly constructed line and facility.
12 | Call-out | 3 | Abdulaziz | Pump DBSE shall be greater than the cartridge seal length to facilitate insitu cartridge seal repair
13 | Text Box | 3 | Abdulaziz | ISO VG 68 shall be considered as an option
14 | Call-out | 3 | Abdulaziz | TR shall confirm with supplier regarding the recommended method of lubrication for VS6 multistage vertical pump.
15 | Callout | 3 | Fernando.Perez | Double check material as Sulphur create corrosion when deposit
16 | Text Box | 4 | Isamu | Dual unpressurized seal flush plan (Plan 52) indicated on FEED is wrong and does not prevent leakage or create alarm upon leakage. 1. Read and understand API 682. 2. Change to Dual pressurized OR single seal and plan 11 and remark to Vendor for confirmation. 3. Apply TCQ for Owner approval for plan 11 and single seal
17 | Text Box | 4 | Abdulaziz | Supplier to ensure providing the venting connection in compliance to API 610 para 6.3.13
18 | Callout | 4 | Fernando.Perez | Acc BMPS-A3 if fluid temperature is above Flash Point but below Self Ingnition Temp single seal to be applied. Check remark # 4 & BMPS-A3
19 | Text Box | 4 | Isamu | 1. Plan M is wrong and does not apply for VS6 pump. 2. This pump does not require cooling plan at all. Accordingly delete all in the cloud and leave it to Vendor
20 | Text Box | 4 | Isamu | All seal Flush shall be pipings (not tubing). Do not alter FEED contractual requirement without Owner approval. Correct accordingly.
21 | Callout | 5 | Fernando.Perez | Acc API 610 Witnessed is HOLD POINT but, Acc BMPS-G-50309 Witnessed is diferent to Hold Point. So use definitions Acc BMPS-G-50309
22 | Text Box | 5 | Isamu | All witness items specified on Feed contractual data sheet shall be restored and respected. Do not alter at your discretion but consult the Owner thru TCQ. Such act is rejected and MOC shall refrain from doing the same over and over
23 | Cloud+ | 6 | 986131 | Who will fill these dimensions.
24 | Call-out | 6 | 986131 | by having the pump below grade review any reliability issues due to rain.
25 | Text Box | 6 | Abdulaziz | 1. TR shall check and confirm with the supplier regarding the provision of lifting lugs for motor and pump. 2. TR Shall considered the removal of pump during normal operation with no disturbance for operation of the stand by pump or other equipment within the same area.
26 | Callout | 8 | Fernando.Perez | Check group should be one
27 | Call-out | 8 | Abdulaziz | Please refer to the instrumentation section in page 4.
28 | Callout | 8 | Sankara | on line
29 | Call-out | 9 | Abdulaziz | Bearing housing & bearings shall be designed for oil mist lubrication in compliance to BMPS G8.
30 | Text Box | 10 | Isamu | Change to Required
31 | Callout | 10 | Fernando.Perez | Acc BMPS-A3 if fluid temperature is above Flash Point but below Self Ingnition Temp single seal to be applied acc temp in Pag 2 Check Seal & Seal System selection in Page 4
32 | Call-out | 10 | Ahmed Ali | correct pump number
33 | Text Box | 10 | Isamu | This remark also has no meaning and relation with upper one. Lubricant list is to be finalized for all project machinery in due course. Delete stuffing
34 | Call-out | 10 | Ahmed Ali | correct
35 | Call-out | 10 | Abdulaziz | Shall be checked and corrected as required
36 | Text Box | 10 | Isamu | Delete this stuffing. There is no cooling water within the battery limit of this pump
37 | Cloud+ | 10 | Sameer Foujdar | INJECTION POINT TO BE BEFORE THE MIXER.
38 | Text Box | 10 | Isamu | This is meaningless confusing comment for Vertical grease lubricated ball bearings motor. Delete or use clear English.