## 050-K-DAT-55001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | General Comment: Always write the full equipment tag no. e.g. 050D1003.
2 | Typewritten Text | 1 | Mohamed Ayyash | General Comment: Equipment number is wrong,replace throughout the document from "050MX5011A/B" to "050MX0011A/B"
3 | Call-out | 1 | Mahdi Ali | Not consistent with other OCs
4 | Cloud+ | 1 | Mohamed Ayyash | Replace the "r" with capital "R"
5 | Text Box | 1 | MAK | S
6 | Cloud+ | 2 | Mohamed Ayyash | Avoid overlap. Can continue on the next line.
7 | Callout | 2 | Fernando.Perez | Components to be described
8 | Cloud+ | 2 | A.Jabbar Mahmood | Correct the SG unit (lb/ft3)
9 | Call-out | 2 | MAK | General Comment: Always write the full equipment tag no. e.g. 050D1003.
10 | Cloud+ | 2 | Mohamed Ayyash | Hidden text
11 | Call-out | 2 | Abdulaziz | Missing information shall be provided
12 | Callout | 2 | Fernando.Perez | Mixer configuration shall permit Seal/Bearing substitution with the tank full
13 | Callout | 2 | Fernando.Perez | Mixing purpose shall be stated
14 | Cloud+ | 2 | Mohamed Ayyash | Overlap. Write away from the box
15 | Cloud+ | 2 | Mohamed Ayyash | Overlap. Write away from the box
16 | Cloud+ | 2 | Mohamed Ayyash | Overlap. Write away from the box
17 | Callout | 2 | Fernando.Perez | Provide space
18 | Callout | 2 | Fernando.Perez | Provide space
19 | Callout | 2 | Fernando.Perez | Provide space
20 | Callout | 2 | Fernando.Perez | Seal and Sealing system should be specified
21 | Call-out | 3 | Abdulaziz | Bearing information shall be provided
22 | Cloud+ | 3 | Mohamed Ayyash | Overlap. Write away from the box
23 | Cloud+ | 3 | Mohamed Ayyash | Overlap. Write away from the box
24 | Cloud+ | 3 | Mohamed Ayyash | Overlap. Write away from the box
25 | Call-out | 3 | 986131 | Refer to BMPS A3 - 7.12.3 applies to other data sheet in this transmittal
26 | Callout | 3 | Fernando.Perez | Sketch of the Tank shall be included to provide tank and connection sizing
27 | Call-out | 4 | Abdulaziz | All operating scenarios to be incorporated for design consideration.
28 | Call-out | 4 | Abdulaziz | Minimum operating level shall be determined and incorporated in the tank design for vendor to design the supporting legs and operation logic accordance to BMPS K11 and API 650.
29 | Call-out | 4 | Abdulaziz | Motor shall be designed to bear with all operating condition.
30 | Call-out | 4 | Ahmed Marhoon | Note 4 to be amended to reflect the actual system. Level is detected by Radar Transmitter and not switches. Stated set points shall be finalized post design development by contractor. Required interfaces with DCS to be in compliance with the final P&ID and BMPS. Contractor to confirm and update the note.
31 | Call-out | 4 | Abdulaziz | Please clarify this statement.
32 | Text Box | 4 | Abdulaziz | Reference to BMPS K11 1. Total Indicated Runout (TIR) of the shaft shall not exceed 2 mils (0.002 inch) at the seal face or stuffing box during operation at design conditions. 2. First critical speed of the shaft shall have a 100% margin above the operating speed.
33 | Call-out | 4 | 986131 | Specify the minimum time available to homogenize as that is the most critical factor.
34 | Cloud+ | 5 | Mohamed Ayyash | Enlarge font in line with other text
35 | Cloud+ | 5 | Mohamed Ayyash | This is a site location and not unit names. It is asking for service for units and therefor need to mention those units names.