## 050-K-DAT-55003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | General Comment: Always write the full equipment tag no. e.g. 050D1001.
2 | Typewritten Text | 1 | Mohamed Ayyash | General Comment: Equipment number is wrong,replace throughout the document from "050MX5013A/B" to "050MX0013A/B"
3 | Cloud+ | 2 | Mohamed Ayyash | Avoid overlap. Can continue on the next line.
4 | Callout | 2 | Fernando.Perez | Components to be described
5 | Cloud+ | 2 | A.Jabbar Mahmood | Correct the SG unit (lb/ft3)
6 | Cloud+ | 2 | Mohamed Ayyash | Hidden text
7 | Call-out | 2 | Abdulaziz | Missing information shall be provided
8 | Callout | 2 | Fernando.Perez | Mixer configuration shall permit Seal/Bearing substitution with the tank full
9 | Callout | 2 | Fernando.Perez | Mixing purpose shall be stated
10 | Typewritten Text | 2 | Nabeel | numbering should be consistent change to "050MX5013A/B"
11 | Cloud+ | 2 | Mohamed Ayyash | Overlap. Write away from the box
12 | Cloud+ | 2 | Mohamed Ayyash | Overlap. Write away from the box
13 | Cloud+ | 2 | Mohamed Ayyash | Overlap. Write away from the box
14 | Callout | 2 | Fernando.Perez | Provide space
15 | Callout | 2 | Fernando.Perez | Provide space
16 | Callout | 2 | Fernando.Perez | Provide space
17 | Callout | 2 | Fernando.Perez | Seal and Sealing system should be specified
18 | Call-out | 3 | Abdulaziz | Bearing information shall be provided
19 | Cloud+ | 3 | Mohamed Ayyash | Overlap. Write away from the box
20 | Cloud+ | 3 | Mohamed Ayyash | Overlap. Write away from the box
21 | Cloud+ | 3 | Mohamed Ayyash | Overlap. Write away from the box
22 | Callout | 3 | Fernando.Perez | Sketch of the Tank shall be included to provide tank and connection sizing
23 | Call-out | 4 | Abdulaziz | All operating scenarios to be incorporated for design consideration.
24 | Call-out | 4 | Abdulaziz | Minimum operating level shall be determined and incorporated in the tank design for vendor to design the supporting legs and operation logic accordance to BMPS K11 and API 650.
25 | Call-out | 4 | Abdulaziz | Motor shall be designed to bear with all operating condition.
26 | Call-out | 4 | Ahmed Marhoon | Note 4 to be amended to reflect the actual system. Level is detected by Radar Transmitter and not switches. Stated set points shall be finalized post design development by contractor. Required interfaces with DCS to be in compliance with the final P&ID and BMPS. Contractor to confirm and update the note.
27 | Call-out | 4 | Abdulaziz | Please clarify this statement.
28 | Text Box | 4 | Abdulaziz | Reference to BMPS K11 1. Total Indicated Runout (TIR) of the shaft shall not exceed 2 mils (0.002 inch) at the seal face or stuffing box during operation at design conditions. 2. First critical speed of the shaft shall have a 100% margin above the operating speed.
29 | Call-out | 4 | 986131 | Specify the minimum time available to homogenize as that is the most critical factor.
30 | Cloud+ | 5 | Mohamed Ayyash | Enlarge font in line with other text
31 | Cloud+ | 5 | Mohamed Ayyash | This is a site location and not unit names. It is asking for service for units and therefor need to mention those units names.