## 050-K-DAT-55006-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Hasan Al Noaimi | BOOSTER
2 | Text Box | 1 | Mahdi Ali | Material Class for the Driver shall follow the Pump, i.e. 'G' in this case. Refer to the Material Class below in the same page.
3 | Text Box | 1 | Mahdi Ali | The Driver equipment tag shall change accordingly
4 | Text Box | 1 | Sameer Foujdar | The right tag numbers for the turbine is 019T0029A/B To be changed in the entire document.
5 | Text Box | 1 | MAK | Use the latest document cover page and API datasheet template which is part of the Homogenization Procedure. MOC Contractor shall coordinate with JV Directorate.
6 | Call-out | 1 | Hasan Al Noaimi | WRONG TAG NUMBER
7 | Text Box | 2 | CK Samy | 113
8 | Text Box | 2 | CK Samy | 50Hz
9 | Text Box | 2 | Mahdi Ali | Remove letter 'f'
10 | Callout | 2 | Yousif Ahmadi | Site: REFINERY TANK FARM
11 | Cloud+ | 2 | Mohamed Ayyash | Use 2/4 (as in page one). Apply to all pages.
12 | Cloud+ | 2 | Mohamed Ayyash | Wrong pump service. See above
13 | Cloud+ | 3 | Mohamed Ayyash | Delete
14 | Cloud+ | 3 | Mohamed Ayyash | Misplaced. Move back in line with other yellow cells
15 | Cloud+ | 3 | Mohamed Ayyash | Missing letter
16 | Cloud+ | 4 | Mohamed Ayyash | ??
17 | Cloud+ | 4 | Mohamed Ayyash | Avoid overlap with table lines.
18 | Cloud+ | 4 | Ahmed Marhoon | Peak 150 has been specified based on the model number mentioned on the BMPS-K5. However, with the Woodward latest model Peak200 available in the market which is replacing Peak150, will Peak150 still be supported and not going to be at the end of its life-cycle by the end of the project? TTSJV to verify with the supplier and advise the client for review and approval. Typical comment. Also, ensure to include BMPS-J18 in addition to other specifications in the RFI.