## 050-L-PPN-55001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | [1] 050-L-PPN-55001-001-Model | Julio.Aguilar | Remove "NEW"
2 | Call-out | [1] 050-L-PPN-55001-001-Model | MAK | General Comment: Use DD.MM.YYYY format for the date, e.g. 25.05.2018
3 | Text Box | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | corresponds
4 | Text Box | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | slope?
5 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Bad design of bund wall. This acute angle will be a natural break point.
6 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Show TO Slepper EL
7 | Callout | [1] 050-L-PPN-55001-001-Model | Abdul Rahim | please note this tank is belong to P&U department. I suggest to be in different drawing. can not mix F050 and U 372
8 | Call-out | [1] 050-L-PPN-55001-001-Model | MAK | Delete F and never use prefixes for Unit Nos.
9 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Move text
10 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Missing sumps & leak detection wells
11 | Callout | [1] 050-L-PPN-55001-001-Model | Berik.Nurbolatov | The road center line thickness should be reduced.
12 | Call-out | [1] 050-L-PPN-55001-001-Model | Mahdi Ali | Continuation shall be made to EPC drawing and not FEED drawing
13 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Include all symbologies & abbreviations
14 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Is this CL of the road or the unit limit as per legend? or both?
15 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Use correct line font
16 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Show HP EL Road for all roads
17 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Show EL TO Bund
18 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Confirm minimum pipe size that will be supported
19 | Text Box | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | relative
20 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | What is happening here? Has the bund wall been lowered by over one meter to allow through traffic? Then what is the point of the rest of the bund wall being EL11.300?
21 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Provide section
22 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | What is happening here? Is there an elevation change?
23 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | H=?
24 | Text Box | [1] 050-L-PPN-55001-001-Model | MAK | General Comment: The latest drawing borders have been submitted to JV Directorate on April 2018. Please use the latest drawing borders that are part of the Homogenisation Procedure.
25 | Text Box | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | slope?
26 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | What is this?
27 | Text Box | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Missing dimensions, & coordinates to locate structures
28 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | New I assume?
29 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Show centerline markers 1 2 3
30 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Show EL
31 | Callout | [1] 050-L-PPN-55001-001-Model | Berik.Nurbolatov | All equipment titles, dimensions data and numbering should be free of line crossing/overlapping.
32 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Maintain correct text height - typical comment
33 | Text Box | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | slope?
34 | Text Box | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | HPP Elevations? Paving type?
35 | Call-out | [1] 050-L-PPN-55001-001-Model | MAK | Delete U372
36 | Call-out | [1] 050-L-PPN-55001-001-Model | MAK | Delete. This is for Bapco use.
37 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Orientation of Northing pointing upward in reference to key plan. For angle conversion, refer to BMP-CON-LET-00047
38 | Call-out | [1] 050-L-PPN-55001-001-Model | Abdulaziz | Lube oil & chemical shelter shall be provided as per BMPS vol 2, sec 6
39 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Not TOS ? Pipe resting on embedded plate?
40 | Callout | [1] 050-L-PPN-55001-001-Model | Berik.Nurbolatov | Please ensure that 3 off decimals are used e.g. EL.xx.xxx
41 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Missing drain slopes, & sump collectors
42 | Call-out | [1] 050-L-PPN-55001-001-Model | Edgardo | It is suggested to exclude this temporary fence from this drawing, which is intended to show only the permanent installations. The temporary fence will soon be removed from site
43 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Missing elevation, & coordinates in road intersections- typ. comments
44 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | How are you planning to put a sleeper here?????
45 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | What is this?
46 | Callout | [1] 050-L-PPN-55001-001-Model | Berik.Nurbolatov | Plot plans shall be dimensioned in metric units (mm) of linear measurement (refer BMPS A8 ‘General guidelines of Plot plan layout Part B Appendix B1
47 | Callout | [1] 050-L-PPN-55001-001-Model | Bernard.Grace | Move location of level to ease reading
48 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | EL to have three digits ie 11.000 - typical comment
49 |  | [1] 050-L-PPN-55001-001-Model | AutoCAD SHX Text | THIS DRAWING
50 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | If these are different ELs then clarify in plan view
51 | Callout | [1] 050-L-PPN-55001-001-Model | Bernard.Grace | Include the nearest Control Stations/Monuments to aid setting out and construction within the plot plan
52 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Move text
53 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Move text to clear drawing
54 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Walkways missing
55 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Confirm that this tank is not bunded
56 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Seperate enrty/exit stairs required
57 | Callout | [1] 050-L-PPN-55001-001-Model | alexis.martinez | General: All Equipment Number need to be updated as per the new numbering provided by owner.
58 |  | [1] 050-L-PPN-55001-001-Model | AutoCAD SHX Text | - C/Arapiles 14, Madrid, Spain
59 | Callout | [1] 050-L-PPN-55001-001-Model | Berik.Nurbolatov | Please mention HPP grade El. relative to site.
60 | Text Box | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | relative
61 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Add note that E & N designate outside of bund wall
62 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Change of EL incorrect location
63 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | HPP
64 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Open ditch drainage?
65 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | H=?
66 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Roadway slopes? Show elevations
67 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | This elevation does not make sense. TO Plinth for tank is EL10.500. TO Bund is EL11.300. Confirm
68 |  | [1] 050-L-PPN-55001-001-Model | AutoCAD SHX Text | The present document or drawing is property of TECHNIP ITALY S.p.A. and shall not, under any circumstances, be totally or partially, directly or indirectly, transferred, reproduced, copied, disclosed or used, without its prior written consent, for any purpose and in any way other than that for which it is specifically furnished or outside the extent of the agreed upon right of use.
69 | Callout | [1] 050-L-PPN-55001-001-Model | Robert.Kawitzki | Why is this bund lower than the surrounding bund? Vlume shall be contained in one bunded area only in case of catastrophic tank failure
70 | Callout | [1] 050-L-PPN-55001-001-Model | Berik.Nurbolatov | Please follow unique legend for "section view ". Refer to the "arrow "used in other unit plot plans
71 | Text Box | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Clarify scope of involved work packages in this unit
72 | Callout | [1] 050-L-PPN-55001-001-Model | Berik.Nurbolatov | Distance& dimension b/n pumps should be shown.
73 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | H=?
74 | Callout | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Clarify pre-cast construction is approved
75 | Call-out | [1] 050-L-PPN-55001-001-Model | MAK | Change L to A which is the correct Material Class for Plot Plan.
76 | Text Box | [1] 050-L-PPN-55001-001-Model | Erwin.Lugue | Missing firefighting facilities, i.e. fire monitors