## 050-M-GAD-55441-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Robert.Kawitzki | 000-A-PPN-60006-001
2 | Callout | 1 | Robert.Kawitzki | 50 Typ
3 | Callout | 1 | Robert.Kawitzki | 9
4 | Text Box | 1 | Robert.Kawitzki | Acronyms, northings and eastings and ELs to be shown as per JV-DI-PIP-004
5 | Callout | 1 | Erwin.Lugue | Check values with the recommended minimum edge distance
6 | Callout | 1 | Robert.Kawitzki | Delete north arrow. Not required and clashes with Orientation 1 & 2
7 | Cloud+ | 1 | MAK | Drawing nos. are incomplete, sheet nos. are missing.
8 | Callout | 1 | Erwin.Lugue | First line to contain document type as per BMPS A8
9 | Text Box | 1 | Erwin.Lugue | General comment: This document needs to be resubmitted with the design calculations. Contractor has to comply with the the civil workflow regarding issuance of documents for review Prior owner approval of all the associated documents for the design are required i.e. plot plan, piping G.A plans, stress loads, etc.
10 | Text Box | 1 | MAK | General Comment: Use the latest drawing borders that are part of the Homogenisation Procedure.
11 | Callout | 1 | Chandrahasan D | Include a column to identify support types (viz anchor supports etc)
12 | Text Box | 1 | Erwin.Lugue | Include Piping G.A. DWGs BPMS-Q-141752 Anchor Bolts Standards
13 | Text Box | 1 | Erwin.Lugue | Indicate in plans & elevations the fixed end connections as per the BMPS-M-50501
14 | Callout | 1 | Erwin.Lugue | Indicate the anchor bolt diameter in accordance with BMPS-Q-141752
15 | Text Box | 1 | Robert.Kawitzki | Letters not used in engineering drawings All letters can be used as revision letters except I, O, Q, S, X and Z. These letters are not allowed because they can be mistaken for numbers or for other letters. For example, a revision letter I can be mistaken for a 1 while an S can be mistaken for a 5. Revision letters must also be uppercase, to minimize confusion between a lowercase "l" and "1" and "I".
16 | Callout | 1 | Mahdi Ali | MATERIAL CLASS FOR PLOT PLAN IS NOT 'L' CHANGE TO 'A' AND CHANGE ALL REFERENCES ACCORDINGLY
17 | Cloud+ | 1 | MAK | NTS
18 | Cloud+ | 1 | MAK | PED
19 | Cloud+ | 1 | MAK | PLAN, ELEVATION & DETAILS STEEL STRUCTURE FOR SLEEPERWAY
20 | Callout | 1 | Erwin.Lugue | Pointer should be on the stiffener plate
21 | Callout | 1 | Erwin.Lugue | Provide a plan layout of the sleeper and where are this frames located
22 | Text Box | 1 | Erwin.Lugue | Provide all abbreviations used in the drawing
23 | Callout | 1 | Erwin.Lugue | Remove this not equal sign symbol
24 | Callout | 1 | Robert.Kawitzki | Show end plate details
25 | Callout | 1 | Chandrahasan D | Show Finished Grade
26 | Callout | 1 | Chandrahasan D | The dwg contents are pipe supports for overhead lines. The term sleeper is misleading verify and modify
27 | Callout | 1 | Erwin.Lugue | Thickness of the wing plates?
28 | Callout | 1 | Erwin.Lugue | This unit
29 | Text Box | 1 | Robert.Kawitzki | TYP
30 | Callout | 1 | Erwin.Lugue | Typical symbology should as per BPMS standard (BMPS-M-50501)
31 | Callout | 1 | Chandrahasan D | Veify fire proofing requirements and show in the drawing
32 | Callout | 1 | Chandrahasan D | Verify clearnce required