## 050-P-HAC-55001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | 2
2 | Call-out | 1 | MAK | 050 - REFINERY TANK FARM
3 | Text Box | 1 | Sankara | 1. Notes which are not relevant for this drawing ( example note 13 &14) shall be removed: Typical comment 2.Hatching to be shown part, for better clarity. Refer to HAC drawing for 7CDU, marked up: Typical Comment 3. Fig 6 of API 505 indicates the zone 0 and zone 1 classifications relevant to the tank, which are not completely reflected in this drawing. Missing details to be shown.
4 | Call-out | 1 | Mahdi Ali | CHAGNE MATERIAL CLASS TO 'A'
5 | Call-out | 1 | MAK | Don't use any letter for Unit Nos.
6 | Call-out | 1 | MAK | General Comment: It's preferred to enter the long form of Unit Name, unless the the field is short. Refer to the Homogenization Procedure for the correct Unit No., Name and format.
7 | Call-out | 1 | MAK | General Comment: Refer to Homogenization Procedure EX and PN number.
8 | Text Box | 1 | MAK | General Comment: The latest drawing borders have been submitted to JV Directorate on April 2018. Please use the latest drawing borders that are part of the Homogenisation Procedure.
9 | Call-out | 1 | MAK | No need to fill these fields
10 | Callout | 1 | Berik.Nurbolatov | Not classified the RHCU Tank area? Please update.
11 | Text Box | 1 | Sankara | The Area Classification shown for these tanks as SAFE is incorrect. Please review and correct.
12 | Text Box | 1 | Raj | This drawing to utilize the most updated Plot Plan for unit 050 after incorporation of Owner comments on the Plot Plan
13 | Callout | 1 | Sankara | Unit numbering shall be as per project tagging system.
14 | Cloud+ | 1 | Mohamed Ayyash | Use revised equipment numbers for unit 934 agreed by JV