## 050-P-INX-55004-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Sankara | Use numbering as per Project Taggiing System
2 | Callout | 2 | Sankara | classifying
3 | Text Box | 2 | Sankara | Reaffirmed, August 2013
4 | Text Box | 3 | Sankara | Provide a title here.
5 | Callout | 3 | alexis.martinez | Include the crude vapour pressure based on crude assay.
6 | Callout | 3 | alexis.martinez | Review the Flash point for Heavy HC High Flash Point. This should be >392 °F
7 | Callout | 4 | Sankara | Clarify the basis of material numbering.
8 | Text Box | 4 | Sankara | Indicate the drawing numbers.
9 | Callout | 4 | alexis.martinez | Review the maximum temperature of crude oil in 050D1001/ 050D1002. Based on Tank Datasheet and 7CDU booster Feed Pump Datasheet, the maximum temperature is 120 °F.
10 | Text Box | 5 | Sankara | Indicate as Pump, Mixer etc. and not Pumps, Mixers: Typical for all equipment.
11 | Callout | 5 | alexis.martinez | Review the maximum temperature on 7CDU Feed Booster Pump. As per Datasheet, the maximum temperature is 120 °F.
12 | Text Box | 5 | Sankara | Indicate the information on degree and availability of ventilation as per API 505 Annexure F
13 | Call-out | 7 | Mahdi Ali | Unit number is yet to be finalized