## 050-Q-PED-55690-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | 4
2 | Cloud+ | 1 | MAK | 0.35417
3 | Text Box | 1 | Mahdi Ali | 62756
4 | Callout | 1 | Mahdi Ali | CHANGE MATERIAL CLASS TO 'A' AND ANDD '-' AFTER THE MATERIAL CLASS
5 | Text Box | 1 | Erwin.Lugue | Culverts drawings
6 | Callout | 1 | Robert.Kawitzki | Dimension sleepers
7 | Text Box | 1 | Mahdi Ali | EN0815
8 | Text Box | 1 | Erwin.Lugue | Finish grade level/ HPP? Paved or gravel?
9 | Text Box | 1 | Erwin.Lugue | Finish grade level? Paved or gravel?
10 | Text Box | 1 | Erwin.Lugue | General comment: This drawing needs to be resubmitted with the calculation reports and could not be properly reviewed/ or issued for construction until the approval of the following basic documents: 1) Basis of Design for Structures & Foundations 2) Final Geotechnical Investigations & Recommendation reports 3) Pile/Deep Foundations Design Criterias, Specifications, and Tests (If applicable) 4) Plot plan 5) Piping Layout
11 | Cloud+ | 1 | Erwin.Lugue | Orientation not according to the key plan
12 | Text Box | 1 | Erwin.Lugue | Piping layout reference DWG
13 | Callout | 1 | Erwin.Lugue | Plant northing?
14 | Text Box | 1 | Erwin.Lugue | Provide all the abbreviations
15 | Text Box | 1 | Erwin.Lugue | Provide overall plot plan
16 | Text Box | 1 | Erwin.Lugue | Provide section
17 | Text Box | 1 | Erwin.Lugue | Provide string dimensions to locate sleepers (i.e. from roads as a reference)
18 | Text Box | 1 | Erwin.Lugue | Reference Coordinates?
19 | Text Box | 1 | Erwin.Lugue | Reference Coordinates?
20 | Text Box | 1 | Erwin.Lugue | Reference Road Coordinates?
21 | Text Box | 1 | Erwin.Lugue | Reference Road Coordinates?
22 | Text Box | 1 | Erwin.Lugue | Reference Road Coordinates?
23 | Text Box | 1 | Erwin.Lugue | References:
24 | Text Box | 1 | Erwin.Lugue | Requires surface drainage of the areas.
25 | Text Box | 1 | Erwin.Lugue | Road & paving plans
26 | Text Box | 1 | Robert.Kawitzki | Show section
27 | Callout | 1 | Robert.Kawitzki | Sleepers not located - typical comment
28 | Text Box | 1 | Erwin.Lugue | Specify sleeper type
29 | Callout | 1 | Robert.Kawitzki | String dimensions to be added to locate all sleepers
30 | Text Box | 1 | Erwin.Lugue | Update with the latest plot plan, U/G, & road and paving layout drawings
31 | Cloud+ | 1 | Erwin.Lugue | Update with the latest revision
32 | Text Box | 1 | Mahdi Ali | USE THE LATEST BORDER THAT IS PART OF THE HOMOGENIZATION PROCEDURE
33 | Callout | 1 | Robert.Kawitzki | We making sleepers of steel? If not, rename TOC