## 050-Q-PED-55690-004-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | 4
2 | Text Box | 1 | Mahdi Ali | 62756
3 | Text Box | 1 | Mahdi Ali | EN0815
4 | Text Box | 1 | Erwin.Lugue | General comment: This drawing needs to be resubmitted with the calculation reports and could not be properly reviewed/ or issued for construction until the approval of the following basic documents: 1) Basis of Design for Structures & Foundations 2) Final Geotechnical Investigations & Recommendation reports 3) Pile/Deep Foundations Design Criterias, Specifications, and Tests (If applicable) 4) Plot plan 5) Piping Layout
5 | Callout | 1 | Berik.Nurbolatov | GENERAL:Dimensional and weight data should be verified and confirmed with piping load study, stress ( where applicable). As well as supporting data are to be clear after piping study. Please advise the calculation basis of the current sleepers size data. At the moment no piping study issued.
6 | Text Box | 1 | Erwin.Lugue | Include in the table: Bottom of footing elevation Finished grade level/ HPP
7 | Callout | 1 | Erwin.Lugue | Plant Northing?
8 | Text Box | 1 | Erwin.Lugue | Provide all the abbreviations
9 | Text Box | 1 | Erwin.Lugue | Provide overall plot plan
10 | Text Box | 1 | Erwin.Lugue | References: Road & paving plan Piping Layout drawings Culvert drawings
11 | Cloud+ | 1 | Erwin.Lugue | Update with the latest revision
12 | Text Box | 1 | Mahdi Ali | USE THE LATEST BORDER THAT IS PART OF THE HOMOGENIZATION PROCEDURE