## 050-Q-PED-55691-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Erwin.Lugue | Finished grade level?
2 | Cloud+ | 1 | Erwin.Lugue | Update key plan with latest plot plan
3 | Text Box | 1 | Erwin.Lugue | Coordinates?
4 | Text Box | 1 | Erwin.Lugue | Specify the sleeper type
5 | Text Box | 1 | Erwin.Lugue | Provide overall plot plan
6 | Text Box | 1 | Erwin.Lugue | String dimensions & reference coordinates?
7 | Text Box | 1 | Mahdi Ali | USE THE UPDATED DRAWING BORDER THAT IS PART OF THE HOMOGENIZATION PROCEDURE
8 | Callout | 1 | mohamed.alaradi | Access platform / stairway??
9 | Callout | 1 | Berik.Nurbolatov | MILLIMETERS
10 | Callout | 1 | Mahdi Ali | 4
11 | Callout | 1 | mohamed.alaradi | space between tank band wall and the pipe-trench not shown.
12 | Text Box | 1 | Erwin.Lugue | String dimensions & reference coordinates?
13 | Text Box | 1 | Erwin.Lugue | General comment: This drawing needs to be resubmitted with the calculation reports and could not be properly reviewed/ or issued for construction until the approval of the following basic documents: 1) Basis of Design for Structures & Foundations 2) Final Geotechnical Investigations & Recommendation reports 3) Pile/Deep Foundations Design Criterias, Specifications, and Tests (If applicable) 4) Plot plan 5) Piping Layout
14 | Cloud+ | 1 | Erwin.Lugue | Orientation not as per key plan
15 | Callout | 1 | Mahdi Ali | MATERIAL CLASS FOR PLOT PLANS IS 'A' AND NOT 'L'. CHANGE THIS AND ALL THE REFERENCES ACCORDINGLY
16 | Text Box | 1 | Erwin.Lugue | Finished grade level?
17 | Text Box | 1 | Erwin.Lugue | Piping Layout DWGs
18 | Callout | 1 | Erwin.Lugue | Road centerline coordinate?
19 | Callout | 1 | Berik.Nurbolatov | Please provide diameter ?
20 | Callout | 1 | Erwin.Lugue | Road centerline coordinate?
21 | Text Box | 1 | Erwin.Lugue | Show surface drainage & flow
22 | Cloud+ | 1 | MAK | 0.35417
23 | Text Box | 1 | Erwin.Lugue | Provide section
24 | Callout | 1 | mohamed.alaradi | Is this an access road to the tanks?? where is the details?