## 050-Q-PED-55691-003-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | 4
2 | Text Box | 1 | Erwin.Lugue | Provide overall plot plan
3 | Text Box | 1 | Mahdi Ali | USE THE UPDATED DRAWING BORDER THAT IS PART OF THE HOMOGENIZATION PROCEDURE
4 | Cloud+ | 1 | Erwin.Lugue | Update key plan with latest plot plan
5 | Callout | 1 | Erwin.Lugue | Plant Northing?
6 | Callout | 1 | Mahdi Ali | MATERIAL CLASS FOR PLOT PLANS IS 'A' AND NOT 'L'. CHANGE THIS AND ALL THE REFERENCES ACCORDINGLY
7 | Text Box | 1 | Erwin.Lugue | General comment: This drawing needs to be resubmitted with the calculation reports and could not be properly reviewed/ or issued for construction until the approval of the following basic documents: 1) Basis of Design for Structures & Foundations 2) Final Geotechnical Investigations & Recommendation reports 3) Pile/Deep Foundations Design Criterias, Specifications, and Tests (If applicable) 4) Plot plan 5) Piping Layout
8 | Cloud+ | 1 | Erwin.Lugue | Millimeters
9 | Text Box | 1 | Erwin.Lugue | References: Road & paving plan Piping Layout DWGs Culvert Drawings