## 051-A-PID-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Abdul Rahim | Delete
2 | Callout | 1 | Mahdi Ali | ADD 'REFRIGERATED'
3 | Callout | 1 | Francis L | Are these multipoint temperature elements? Consider adding to this Note.
4 | Callout | 1 | Francis L | Clarify function / number of switches.
5 | Text Box | 1 | Edgardo | Comments that would be generated and agreed upon during the Joint PID review between Bapco and TTSJV shall be incorporated in the applicable sheets of Unit 051 PID. This comment applies to all sheets of Unit 051 PID
6 | Text Box | 1 | A Albalooshi | General comment: All applicable comments generated and agreed upon during the Joint PID Review between ROC and Owner shall be incorporated in the next update of the respective documents.
7 | Text Box | 1 | Francis L | General note: All instrumentation connections (impulse lines, manifolds, etc) where applicable shall be insulated as per line insulation requirements.
8 | Callout | 1 | Francis L | How are these measurements displayed (multi readings, average, etc)?
9 | Callout | 1 | Mahdi Ali | INCORRECT OPC TYPE
10 | Callout | 1 | Abdul Rahim | more details to be shown by tank MFR
11 | Call-out | 1 | Edgardo | Please clarify if there is specific required elevation above the highest adjacent platform
12 | Callout | 1 | Francis L | Please clarify.
13 | Callout | 1 | Abdul Rahim | Pls discuss requirement for Isolation of each line
14 | Callout | 1 | Francis L | Provide tag no. of PC
15 | Callout | 1 | Francis L | PULL instead of PUSH
16 | Text Box | 1 | Mahdi Ali | THIS APPLICABLE FOR ALL THE PIDS. 1. TAG NUMBER FOR THE DRIVER FOR ROTATING EQUIPMENT SUCH AS PUMPS OR COMPRESSORS SHALL BE INSERTED ON ALL PIDS AS PER BMPS-A8 SECTION 8.4.3. 2. USE UPDATED LINE TYPE FOR FIELDBUS SIGNAL. 3. MAKE SURE THAT CORRECT OPC TYPE IS USED FOR UTILITIES AND PROCESS 4. EQUIPMENT TAG SHALL NOT CONTAIN SPACES.
17 | Callout | 1 | Abdul Rahim | Type of roof to be identified by tank MFR
18 | Callout | 1 | Abdul Rahim | why there is no by pass
19 | Callout | 1 | Abdul Rahim | why there is no root valve