## 051-A-PID-00021-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Abdul Rahim | Refrigerated
2 | Call-out | 1 | Abdul Rahim | Pls be consistent either C3 or Propane
3 | Text Box | 1 | Francis L | General note: All instrumentation connections (impulse lines, manifolds, etc) where applicable shall be insulated as per line insulation requirements.
4 | Callout | 1 | Francis L | Show direction of drift (open or close?) as per BMPS-A-50003
5 | Callout | 1 | Francis L | Two solenoid valves (2oo2 voting) shall be used for ESD to trip control valve. Refer to Typical 3 of sht 13 of BMPS-A-50003
6 | Callout | 1 | Francis L | PDG instead
7 | Text Box | 1 | MAK | 051M0004A
8 | Text Box | 1 | Edgardo | Comments that would be generated and agreed upon during the Joint PID review between Bapco and TTSJV shall be incorporated in the applicable sheets of Unit 051 PID. This comment applies to all sheets of Unit 051 PID
9 | Text Box | 1 | Abdul Majeed | Drain valve to be installed upstream of CV AFVO as per BMPS-A-5003
10 | Text Box | 1 | Mahdi Ali | THIS APPLICABLE FOR ALL THE PIDS. 1. TAG NUMBER FOR THE DRIVER FOR ROTATING EQUIPMENT SUCH AS PUMPS OR COMPRESSORS SHALL BE INSERTED ON ALL PIDS AS PER BMPS-A8 SECTION 8.4.3. 2. USE UPDATED LINE TYPE FOR FIELDBUS SIGNAL. 3. MAKE SURE THAT CORRECT OPC TYPE IS USED FOR UTILITIES AND PROCESS 4. EQUIPMENT TAG SHALL NOT CONTAIN SPACES.
11 | Callout | 1 | Francis L | Clarify the condition giving the permissive.
12 | Text Box | 1 | MAK | General Comment to be applied to all P&IDs: As per BMPS-A8, Section 8.4.3, Drivers Tag Nos. e.g. Motors/Turbines shall always be inserted in all P&IDs and placed below the parent equipment no. e.g. Pump/Fan/Mixer/Cooler where possible. Motor FinFan tag nos. shall always be shown where applicable.
13 | Call-out | 1 | Abdul Rahim | Delete
14 | Callout | 1 | Francis L | Remove LL
15 | Callout | 1 | Francis L | Tag no. to have double suffix. Refer to BMPS-J3.