## 051-A-PID-00023-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Francis L | Clarify the need for bridles. Refer to BMPS-A-50003.
2 | Callout | 1 | Francis L | case
3 | Text Box | 1 | Abdul Majeed | Drain valve to be installed upstream of CV AFVO as per BMPS-A-5003
4 | Callout | 1 | Francis L | This note is against an LIT. Clarify correctness.
5 | Callout | 1 | Francis L | Indicate direction of drift
6 | Call-out | 1 | MAK | Add REFRIGERATED
7 | Callout | 1 | Francis L | Indicate type of bridle configuration detail.
8 | Callout | 1 | Francis L | Clarify location of FV.
9 | Callout | 1 | Francis L | Use two letter suffix. Refer BMPS-J3
10 | Callout | 1 | Francis L | Remove alarms
11 | Callout | 1 | Francis L | Clarify requirement for one solenoid valve instead of two.
12 | Callout | 1 | Francis L | forced to Manual and drive the controller output to safe position.
13 | Callout | 1 | Francis L | General: Letters "I" and "O" shall not be used for tag suffixes.
14 | Cloud+ | 1 | MAK | Delete
15 | Callout | 1 | Francis L | Should this read as valve?
16 | Callout | 1 | Francis L | Is the ESD required to force the LC to MAN and drive the controller to safe position?
17 | Callout | 1 | Francis L | PDG
18 | Callout | 1 | Francis L | Clarify the type (MAG) of LIT.
19 | Callout | 1 | Francis L | Clarify requirement for online testing ie. is bypass required?
20 | Callout | 1 | Francis L | Indicate tag no.