## 051-A-PID-00041-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Abdul Rahim | where will be the location of pump start and stop buttons
2 | Call-out | 1 | Abdul Rahim | what kind of level transmiter
3 | Call-out | 1 | Abdul Rahim | Pls explain this set up
4 | Call-out | 1 | Abdul Rahim | why 24" consider entery for maintenance for tank T&I. Need another manway
5 | Call-out | 1 | Abdul Rahim | Provide space on plot plan for a spare tank
6 | Callout | 1 | Francis L | Describe as "Low level rising"
7 | Text Box | 1 | MAK | General Comment to be applied to all P&IDs: As per BMPS-A8, Section 8.4.3, Drivers Tag Nos. e.g. Motors/Turbines shall always be inserted in all P&IDs and placed below the parent equipment no. e.g. Pump/Fan/Mixer/Cooler where possible. Motor FinFan tag nos. shall always be shown where applicable.
8 | Call-out | 1 | Abdul Rahim | Pls discuss requirement for spill back
9 | Cloud+ | 1 | MAK | Use the correct Bapco document number.
10 | Callout | 1 | Francis L | Clarify type
11 | Text Box | 1 | MAK | 051M0012A
12 | Callout | 1 | Francis L | Remove level descriptions on P&ID.
13 | Text Box | 1 | MAK | 051M0012B
14 | Call-out | 1 | Abdul Rahim | Tank details needs to be shown. Is there any data sheet specification for this tank