## 051-A-PID-00042-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Abdul Rahim | to be as per Bapco standard drawing i.e shaded tank for eye wash and shower
2 | Callout | 1 | Francis L | Clarify arrows
3 | Call-out | 1 | Abdul Rahim | and provide a small water tank with shade as per Bapco standard drawing
4 | Call-out | 1 | Abdul Rahim | Pls discuss allow space for container
5 | Call-out | 1 | Abdul Rahim | is there any requirement for pump out pump
6 | Call-out | 1 | Abdul Rahim | capcacity to be adequate to avoid frequent filling