## 051-A-PPN-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | AliRedha Malalla | * Reference to Maintenance Consideration Report para 5.2.1; overhead crane shall be considered for both compressor trains. * Both trains to be under shelter. * Sufficient room to be considered for suction and discharge pipes removal.
2 | Cloud+ | 1 | MAK | 051 - REFRIGERATED LPG C3/C4 STORAGE FACILITY AT WHARF
3 | Callout | 1 | Chandrahasan D | Please note the comments on coordinates and elevations in the general notes. Modify accordingly. Typical for all elevations
4 | Call-out | 1 | Edgardo | Refer to comment in 051-A-PPN-00001-001 regarding provision of sufficient access to equipment during maintenance work as well as on the segregation of the two trains of the Refrigeration Facilities, during T&I work on one train while the other train is in operation
5 | Callout | 1 | Mahdi Ali | TAGS SHALL NOT CONTAIN AREA CODE
6 | Callout | 1 | Chandrahasan D | This coordinates and elevation apply to Sitra Tank farm only and Not for Wharf area. Wharf area use UTM coordinates and NSD.
7 | Cloud+ | 1 | MAK | Use short description C3/C4 AT WHARF