## 051-A-STS-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | REFRIGERATED LPG C3/C4 STORAGE FACILITY AT WHARF
2 | Callout | 1 | Mahdi Ali | THIS DOCUMENT IS A CALCULATION SHEET AND NOT A STUDY. THUS THE DOCUMENT TYPE SHALL BE 'CAL' AND NOT 'STS'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A STUDY THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY.
3 | Callout | 1 | Mahdi Ali | INCORRECT UNIT DESCRIPTION
4 | Text Box | 1 | MAK | Bapco has not received the Unit Equipment List (Item Index) for review. How to cross check the correctness/completeness of equipment numbers within this document?? Equipment List is the master index and shall be issued before issuing this document.
5 | Cloud+ | 2 | MAK | Why 051P0008/0009 are not used?
6 | Cloud+ | 2 | MAK | Why 051U0009 is not used?
7 | Cloud+ | 2 | MAK | B
8 | Typewritten Text | 3 | steven.coyne | Please add reference to source procedure :000-A-PRO-50017-001 Criticality Procedure
9 | Text Box | 3 | MAK | General Comment: Equipment List for Unit 051 was not issued for review. However, this list shall perfectly match Unit 051 - Equipment List (Item Index). All Units equipment shall be included for Criticality Rating Evaluation.
10 | Callout | 3 | A Albalooshi | HSE impact for propane compressor suction drum, propane condenser train A&B, shall be re- evaluated as flammable liquids are handled. Also in terms of cost impact there will be a significant direct and indirect unavailability and replacement cost and time of asset or equipment. Equipment installation needs also to reviewed as complexity of the site conditions is foreseen.
11 | Text Box | 3 | A Albalooshi | Please relate the criticality ratings with the inspection levels.