## 051-C-DAT-00003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 2 | A Albalooshi | LTCS
2 | Text Box | 3 | Edgardo | Please clarify requirement for insulation as well as for insulation support; as per PID, these vessels will be insulated
3 | Callout | 5 | A Albalooshi | Line sizes in the P&IDs are preliminary and this shall be finalized along with Hydraulic calculations during detailed engineering stage of the EPC “The sizes are minimum in the P&IDs”. This document shall be updated after unfreezing the “HOLD” from the P&IDs.