## 051-E-DAT-00002-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Abdul Rahim | I checked with Banagas their experience with air cooler. they stated that it is better to over size the cooler because in hot and humid summer day they experience problem controlling temperature
2 | Cloud+ | 1 | MAK | REFRIGERATED LPG C3/C4 STORAGE FACILITY AT WHARF
3 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
4 | Text Box | 2 | Mohamed Aldoseri | general details of the drivers shall be filled on this data sheet-typical to all air coolling heat exchangers data sheets
5 | Text Box | 2 | AliRedha Malalla | Please change to "HTD" according to BMPS-E7
6 | Call-out | 3 | Jawad Alawi | Specified material is not adequate for this temperature
7 | Text Box | 3 | Mohamed Aldoseri | Typical to all similar data sheets
8 | Text Box | 3 | Mohamed Aldoseri | -total nos. of drivers shall be provided in the notes. -Fans Driver data sheets shall be submitted.