## 051-G-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Call-out | 1 | MAK | REFRIGERATED
3 | Call-out | 2 | MAK | Add on all pages REFRIGERATED
4 | Callout | 2 | Abdul Rahim | Pls ensure the pump rate is not less than propane rundown from unit 005
5 | Text Box | 4 | Isamu | Tubing is not acceptable as repeatedly commented and discussed. Piping, flanges and socket welding shall be applied to plan 52 and 13 as per the data sheet.
6 | Callout | 5 | A Albalooshi | Required
7 | Callout | 5 | A Albalooshi | Required
8 | Text Box | 8 | Isamu | To be confirmed by Pump Vendor. "We do not communicate with any but Pump Vendor"
9 | Text Box | 8 | Isamu | Delete this meaningless remark because for this specific type of pump, both NPSHA and NPSHR will be decided by Vendor including the desired margin of BMPS-G