## 051-S-GAD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | Consider changing the title to the following: GENERAL ARRANGEMENT DRAWING GENERAL UNDERGROUND NETWORKS FOR 051 - C3/C4 WHARF MAJOR UG
2 | Text Box | 1 | Chandrahasan D | The legend are not consistent between the operating center drawings. Suggested to have consistent Legend for the whole project.
3 | Cloud+ | 1 | MAK | Fill in EX and PN nos.
4 | Text Box | 1 | Chandrahasan D | What about LAN, Telephone u/g cable network?
5 | Call-out | 1 | Edgardo | The sanitary sewage pump is no longer required; refer to comment on 051 General Plot Plan.
6 | Cloud+ | 1 | MAK | C3/C4 WHARF
7 | Callout | 1 | Francis L | Indicate relevant building numbers.
8 | Text Box | 1 | Francis L | Please include all instrument cable routing details as none are not shown on this drawing.
9 | Text Box | 1 | Edgardo | Please incorporate any required changes in this U/G drawing due to any potential changes in the Plot Plan, which was reviewed and commented under transmittal BMP-ROC-TRI-00412
10 | Cloud+ | 1 | MAK | Use the correct Substation no.
11 | Cloud+ | 1 | MAK | Align the vertical lines
12 | Callout | 1 | Chandrahasan D | This coordinate system and elevation applies to SITRA TANK FARM only. Use UTM coordinates and NSD for this area.
13 | Call-out | 1 | Edgardo | In lieu of providing a separate septic tank, please consider routing the sanitary sewage from Gate House to the septic tank near the control room.
14 | Callout | 1 | Chandrahasan D | Manholes to have Unique Identification Numbers
15 | Callout | 1 | Francis L | Ensure all access areas to building are paved,
16 | Call-out | 1 | Edgardo | Please change "Empty" to "Emptied"