## 056-A-PID-00003-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | 056M2992
2 | Text Box | 1 | MAK | 056M2993
3 | Callout | 1 | Francis L | Delete suffix A as this tag function (FI) is unique.
4 | Call-out | 1 | MAK | General Comment to be applied to all P&IDs: As per BMPS-A8, Section 8.4.3, Drivers Tag Nos. e.g. Motors/Turbines shall always be inserted in all P&IDs and placed below the parent equipment no. e.g. Pump/Mixer/Cooler where possible.
5 | Text Box | 1 | Omran A | Hazop 3 to confirm if remote stop switch 15 m away from Pumps located at Tank Farm is required.
6 | Callout | 1 | Francis L | Indicate Note 7 against this tag as it is associated with stopping the pump when target quantity is achieved.
7 | Callout | 1 | Francis L | Indicate Note 7 against this tag as it is associated with stopping the pump when target quantity is achieved.
8 | Typewritten Text | 1 | Nabeel | It has been confirmed that new pumps will purchased and the existing are not available
9 | Call-out | 1 | Abdul Rahim | new pumps to be installed
10 | Call-out | 1 | Edgardo | Please assign a dedicate line number for this branch line
11 | Call-out | 1 | Edgardo | Please assign a dedicated line number for the manifold
12 | Call-out | 1 | Edgardo | Please change MTBE to 056P2993/P2994
13 | Call-out | 1 | Edgardo | Please indicate the size of the reducer, after the size of the control valve is confirmed
14 | Call-out | 1 | Edgardo | Please indicate the size of the reducers
15 | Call-out | 1 | Edgardo | Please provide valve
16 | Call-out | 1 | Abdul Rahim | since there is no control valve on pump discharge, how to ensure no flow of MTBE to gasoline tanks.
17 | Typewritten Text | 1 | Nabeel | The are no existing MTBE lines
18 | Call-out | 1 | Abdul Rahim | To be confirmed if D 915 can be used for MTBE (riveted tank)