## 056-A-PID-00008-001-R12A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | Add the above note below the drawing number as was originally provided by Bapco. Do not remove this note from all the PID provided by Bapco.
2 | Call-out | 1 | Abdul Rahim | existing tie in to be checked at site if available and in suitable location
3 | Call-out | 1 | Abdul Rahim | why no isolating valve
4 | Call-out | 1 | Edgardo | Upon confirmation at site of this tie-in, the existing 1 1/2" drain may not be required
5 | Call-out | 1 | Edgardo | Please relocate the tie-in point to the 8" flange and provide isolating valves, subject to confirmation during site visit. In the existing PID, there are no reducers and valves
6 | Call-out | 1 | Abdul Rahim | to be checked at site if available
7 | Call-out | 1 | Abdul Rahim | Hot Oil to Where ?
8 | Call-out | 1 | Abdul Rahim | existing tie in to be checked at site if available and in suitable location
9 | Call-out | 1 | Abdul Rahim | Hot Oil from where ?
10 | Text Box | 1 | Mahdi Ali | THIS DRAWING IS CONVERTED FROM BRA031504-001