## 056-A-PID-00010-003-R4A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Edgardo | These 2" valves shall be shown with blinds, not plugs
2 | Text Box | 1 | Mahdi Ali | Add the above note below the drawing number as was originally provided by Bapco. Do not remove this note from all the PID provided by Bapco.
3 | Call-out | 1 | Edgardo | The tie-in shall be direct to the flange. Subject to confirmation during site verification
4 | Text Box | 1 | Edgardo | Refer to comment on 056-A-PID-00004-001 regarding size of drain valves on the new lines
5 | Text Box | 1 | Mahdi Ali | THIS DRAWING IS CONVERTED FROM BRA080051-003