## 056-A-PID-00013-003-R4A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | Add the above note below the drawing number as was originally provided by Bapco. Do not remove this note from all the PID provided by Bapco.
2 | Call-out | 1 | Abdul Rahim | not clear is it via # 5 and # 13 sealines
3 | Call-out | 1 | Edgardo | These drain valves shall be shown with blinds, instead of plugs
4 | Call-out | 1 | Edgardo | Please provide a dedicated line number for this branch line
5 | Call-out | 1 | Edgardo | Please consider using line P1382 for this line, instead of of P1194 which is the branch line
6 | Call-out | 1 | Edgardo | Please confirm line size
7 | Call-out | 1 | Edgardo | These drain valves shall be shown with blinds, instead of plugs
8 | Text Box | 1 | Mahdi Ali | THIS DRAWING IS CONVERTED FROM BRA080055-003