## 056-A-PID-00014-002-R4A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | Add the above note below the drawing number as was originally provided by Bapco. Do not remove this note from all the PID provided by Bapco.
2 | Call-out | 1 | Edgardo | These drain valves shall be shown with blind, instead of plug
3 | Call-out | 1 | Edgardo | This drawing number format is already changed
4 | Call-out | 1 | Edgardo | Please provide these lines with vent and drain valves
5 | Text Box | 1 | Mahdi Ali | THIS DRAWING IS CONVERTED FROM BRA080056-002
6 | Call-out | 1 | MAK | Delete space.
7 | Call-out | 1 | Edgardo | Please change offpage connector to Sheet 004
8 | Call-out | 1 | Edgardo | Please provide this line with 1" vent
9 | Call-out | 1 | MAK | Delete all + signs