## 056-A-PID-00014-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Edgardo | These drain valves to be provided with blinds, instead of plugs
2 | Call-out | 1 | Mahdi Ali | THIS DRAWING NUMBER IS AVAILABLE IN BAPCO SYSTEM. USE 056-A-PID-00014-004. CHAGNE ALL OPCs ACCORDINGLY
3 | Call-out | 1 | Edgardo | Please change to 056P2958
4 | Callout | 1 | Francis L | Indicate Note 22 against the level tag which is associated with the DCS logic sequence in stopping the mixer motors.
5 | Call-out | 1 | MAK | Move the tag to a proper place.
6 | Text Box | 1 | MAK | 056M5607C
7 | Text Box | 1 | MAK | 056M5607A
8 | Text Box | 1 | MAK | 056M5607B
9 | Call-out | 1 | Edgardo | Please change to 056P3099
10 | Call-out | 1 | MAK | Delete spaces between the suffixes.
11 | Call-out | 1 | Edgardo | Please change to 056P3577
12 | Call-out | 1 | MAK | General Comment to be applied to all P&IDs: As per BMPS-A8, Section 8.4.3, Drivers Tag Nos. e.g. Motors/Turbines shall always be inserted in all P&IDs and placed below the parent equipment no. e.g. Pump/Mixer/Cooler where possible.