## 056-A-PID-00015-003-R6A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | Add the above note below the drawing number as was originally provided by Bapco. Do not remove this note from all the PID provided by Bapco.
2 | Call-out | 1 | Abdul Rahim | refer to previous comment
3 | Call-out | 1 | Edgardo | Please show the stream name
4 | Call-out | 1 | Edgardo | Please transfer Note 12 to 056D723
5 | Call-out | 1 | Edgardo | Please change size of drain valve to 1 1/2" as line size is > 16", per BMPS-L-144014
6 | Call-out | 1 | Edgardo | The drain valve shall be provided with blind instead of plug
7 | Text Box | 1 | Mahdi Ali | THIS DRAWING IS CONVERTED FROM BRA080057-003