## 056-A-PID-00015-004-R6A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | Add the above note below the drawing number as was originally provided by Bapco. Do not remove this note from all the PID provided by Bapco.
2 | Cloud+ | 1 | Edgardo | The 4" stub is no longer required, since the existing filling line is already provided with 4" stub for initial filling
3 | Call-out | 1 | Edgardo | Please interchange the position of the vent and drain valves
4 | Call-out | 1 | Abdul Rahim | same comment on tank 733
5 | Text Box | 1 | Mahdi Ali | THIS DRAWING IS CONVERTED FROM BRA080057-004
6 | Text Box | 1 | AliRedha Malalla | branch
7 | Call-out | 1 | Abdul Rahim | is it TE-0272 or TE-1272