## 056-A-PID-00018-001-R5A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DRAWING IS CONVERTED FROM BRA080062-001
2 | Call-out | 1 | Edgardo | Please revise stream name, to be consistent with the stream name shown in 056-A-PID-00021-001
3 | Call-out | 1 | Abdul Rahim | Post BMP is not in DSL service
4 | Text Box | 1 | Francis L | PLC tags shall be redrawn as DCS tags.
5 | Text Box | 1 | Mahdi Ali | Add the above note below the drawing number as was originally provided by Bapco. Do not remove this note from all the PID provided by Bapco.
6 | Text Box | 1 | Edgardo | Please provide connection of S/L # 15 and S/L # 16 to the 14" WD Line shown in 056-A-PID-00019-001 that will be used for the crude importation