## 056-A-PID-00019-001-R4A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Francis L | Indicate as analog instead of FF signal.
2 | Text Box | 1 | Mahdi Ali | Add the above note below the drawing number as was originally provided by Bapco. Do not remove this note from all the PID provided by Bapco.
3 | Call-out | 1 | Edgardo | Please provide these lines with vent and drain valves
4 | Call-out | 1 | Abdul Rahim | improve on label name
5 | Call-out | 1 | Edgardo | Please confirm the 12" line size
6 | Call-out | 1 | Edgardo | Please indicate line number, which is shown as 056-34"-P1012-B30-N in 056-A-PID-00019-002
7 | Call-out | 1 | Edgardo | Please provide this line with vent and drain valves
8 | Call-out | 1 | Edgardo | Please mode this tie-in after the check valve and isolating valve.
9 | Text Box | 1 | Mahdi Ali | THIS DRAWING IS CONVERTED FROM BRA080063-001