## 056-A-PPN-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mohamed Aldoseri | - ADD 1 COLOUMN INTO THE TABLE AND LIST DRIVERS DETAILS WHERE APPLICABLE - ALL EQUIPMENTS POST BMP SHALL BE LISTED IN THE ABOVE TABLE; ie. TANKS.
2 | Cloud+ | 1 | MAK | 1.7778
3 | Cloud+ | 1 | MAK | Change to 2
4 | Cloud+ | 1 | MAK | Change to: 056D0761
5 | Cloud+ | 1 | MAK | Change to: 056D0761
6 | Cloud+ | 1 | MAK | Change to: 056OMG5601
7 | Cloud+ | 1 | MAK | Change to: 056P5627A/B
8 | Cloud+ | 1 | MAK | Change to: OMG PACKAGE 056OMG5601
9 | Cloud+ | 1 | MAK | Change Unit to: 056 - SITRA TANK FARM
10 | Call-out | 1 | Mohamed Aldoseri | HAZARDOUS AREA CLASSIFICATION DRAWINGS TO BE INCLUDED IN THE REFERENCE LIST
11 | Call-out | 1 | Edgardo | In the as built revision, only the equipment tag number shall be shown. This comment applies wherever the text "BMP ...." is shown on the BMP facilities
12 | Callout | 1 | Sankara | Indicate the existing Sitra Main Substation
13 | Callout | 1 | Abdul Rahim | MTBE pumps now new pumps.
14 | Text Box | 1 | Robert.Kawitzki | Refer to 000-A-PPN-60006-001
15 | Cloud+ | 1 | MAK | Revise the description and the number.
16 | Call-out | 1 | Mohamed Aldoseri | SITRA 50 Hz SUBSTATION
17 | Callout | 1 | Mahdi Ali | SITRA TANK FARM PLOT PLAN IS AN EXISTING DRAWING AND MUST NOT BE RE-NUMBERED. JV REQUESTED THIS DRAWING AND IT WAS COMMUNICATED TO THEM. JV SHALL MODIFY THE EXISTING DRAWING.
18 | Callout | 1 | Chandrahasan D | Sitra tank local coordinates and datum are different from Refinery local coordinates and datum. Verify Bapco correspondence on this and modify
19 | Cloud+ | 1 | MAK | The tag nos. for these pumps have been changed as follows: 056P5627A 056P5627B And their driver tag nos. changed to: 056M5627A 056M5627B
20 | Text Box | 1 | Ahmed Habib | This is existing: Sitra Tank Farm Control Building
21 | Call-out | 1 | Edgardo | This list includes only the new BMP equipment and does not include the existing equipment to be retained post BMP; Please clarify and update list as necessary
22 | Callout | 1 | Robert.Kawitzki | True North
23 | Call-out | 1 | Mohamed Aldoseri | TYPICAL COMMENTS: - PROPER DESCIPTION SHALL BE USED. (ie. 056P5603 - NAPHTHA SHIPPING PUMP). - USE COMPLETE TAGGING NUMBER TO AVOID CONFUSION.