## 056-A-STS-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Bapco has not received the Unit Equipment List (Item Index) for review. How to cross check the correctness/completeness of equipment numbers within this document?? Equipment List is the master index and shall be issued before issuing this document.
2 | Callout | 1 | Mahdi Ali | THIS DOCUMENT IS A CALCULATION SHEET AND NOT A STUDY. THUS THE DOCUMENT TYPE SHALL BE 'CAL' AND NOT 'STS'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A STUDY THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY.
3 | Callout | 2 | Abdul Rahim | also confirm if riveted tank is suitable for MTBE
4 | Text Box | 2 | A Albalooshi | Please relate the criticality ratings with the inspection levels.
5 | Text Box | 2 | MAK | General Comment: Equipment List for Unit 056 was not issued for review. However, this list shall perfectly match Unit 056- Equipment List (Item Index). All Units equipment shall be included for Criticality Rating Evaluation.
6 | Typewritten Text | 2 | steven.coyne | aDD REFERENCE TO PROCEDURE : Criticality Rating 000-A-PRO-50017-001
7 | Cloud+ | 2 | MAK | Change to: 056P5627A 056P5627B
8 | Callout | 2 | Abdul Rahim | correct this, new pumps will be used
9 | Callout | 2 | A Albalooshi | HSE impact for MTBE pumps can be re-evaluated
10 | Callout | 2 | A Albalooshi | HSE considerations for MTBE tanks can be revised.