## 056-G-DAT-50002-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Callout | 2 | Mahdi Ali | 056 - SITRA TANK FARM
3 | Text Box | 2 | Mohamed Aldoseri | X
4 | Call-out | 2 | Mohamed Aldoseri | Area classification shall be confirmed after the final HAC drawing, considering API 500 as indicated in BMPS-P2- Typical to all pumps/motors in existing areas.
5 | Call-out | 2 | Mohamed Aldoseri | Provide the correct starting method, D.O.L in most cases-Typical comment for all pumps data sheets
6 | Callout | 8 | Mahdi Ali | ADD UNIT NUMBER TO THE EQUIPMENT TAG
7 | Callout | 8 | Abdul Rahim | should be "yes" in case of crude