## 056-G-DAT-50003-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | David.Jimenez | LV motors datasheets will be attached to MR as blank form to be filled in by Vendor during engineering, as they will be purchased under umbrella contract.
2 | Call-out | 1 | Mohamed Aldoseri | Equipment service description (KEROSENE) shall be SIMILAR to other related documents such as consumer list and SLD-TYPICAL
3 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
4 | Call-out | 2 | Mohamed Aldoseri | To be confirmed with hazardous area classification drawing-TYPICAL
5 | Callout | 2 | A Albalooshi | Under Roof?
6 | Callout | 3 | A Albalooshi | APPI 610 compliant
7 | Callout | 3 | A Albalooshi | Please advise why hydraulic fit is not required. This was in FEED Data sheet
8 | Text Box | 4 | Isamu | Plan 13 is for volatile saturated and low specific gravity liquid. It is not suitable for this application. Change to self flushing (plan 11) and confirm suitability with pump/seal maker.
9 | Callout | 4 | A Albalooshi | Please confirm that single arrangement is adequate for this requirement
10 | Callout | 4 | Danut.Dragan | For this critical pump, accelerometers are not acceptable. Axial, Radials, Key-phaser and Temperature Sensors should be provided. Please align with BMPS-A3, BMPS-G1.
11 | Text Box | 4 | Isamu | Accelerometer is a device highly sensitive to wide range of frequencies and may frequently generate false alarms and readings due to frequencies produced not by the pump. Consider employing velocity pick up, on motor stand on motor body and consult the Vendor on this issue
12 | Callout | 5 | A Albalooshi | Required as per FEED data sheets
13 | Callout | 5 | A Albalooshi | Required as per FEED data sheets
14 | Text Box | 6 | Isamu | The purpose of such under ground vertical double casing VS6, is solely for limited or no enough NPSHA. Since your NPSHA is 30 ft , then the application can much likely be covered by the much simpler type BB2. Please revisit this issue with process and other group.
15 | Text Box | 8 | AliRedha Malalla | apply