## 056-G-DAT-50004-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS DATASHEET TEMPLATE WAS REVISED AND WILL BE ISSUED WITH THE HOMOGENIZATION PROCEDURE. IN THE NEXT REVISION, THE REVISED TEMPLATE AND COVER PAGE SHALL BE USED.
2 | Callout | 1 | David.Jimenez | LV motors datasheets will be attached to MR as blank form to be filled in by Vendor during engineering, as they will be purchased under umbrella contract.
3 | Call-out | 2 | Mohamed Aldoseri | Confirm as per hazardous area classification drawing-typical
4 | Callout | 3 | A Albalooshi | API 610 compliant
5 | Callout | 3 | A Albalooshi | Please advise why hydraulic fit is not required. This was in FEED Data sheet
6 | Text Box | 4 | Isamu | Plan 13 is for volatile saturated and low specific gravity liquid. It is not suitable for this application. change to self flushing (plan 11) and confirm suitability with pump/seal maker. Also justify altering the dual mech seal required by FEED DS.
7 | Text Box | 4 | Isamu | Accelerometer is a device highly sensitive to wide range of frequencies and may frequently generate false alarms and readings due to frequencies produced not by the pump. Consider employing velocity pick up, on motor stand on motor body and consult the Vendor on this issue
8 | Callout | 4 | A Albalooshi | Please confirm that single arrangement is adequate for this requirement
9 | Callout | 5 | A Albalooshi | Required as per FEED data sheets
10 | Callout | 5 | A Albalooshi | Required as per FEED data sheets
11 | Text Box | 6 | Isamu | Add this remark: To minimize the length of the pump and reduce numbers of line shaft bearings, double suction first stage impeller or employment of inducer shall be considered.