## 056-L-INX-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | THIS IS AN EXISTING UNIT AND ALL THE LINE NUMBERS SHALL BE OBTAINED FROM BAPCO. TTSJV SHALL SEND OFFICIAL REQUEST FOR A BLOCK OF NUMBERS TO BE UTILIZED FOR EACH FLUID CODE.
2 | Text Box | 2 | MAK | Add Bapco Doc. No. on all pages
3 | Callout | 2 | Mahdi Ali | LINE NUMNER SHOULD NOT INCLUDE THE FLUID CODE
4 | Call-out | 3 | Edgardo | These pumps will be replaced with new numbers; please refer to related comment on the PID
5 | Call-out | 5 | Edgardo | Please confirm the C32 pipe spec; in 056-A-PID-00015-004, pipe P1113 is shown as B30 pipe spec
6 | Text Box | 9 | A Albalooshi | Line sizes in the P&IDs are preliminary and this shall be finalized along with Hydraulic calculations during detailed engineering stage of the EPC “The sizes are minimum in the P&IDs”. This document shall be updated after unfreezing the “HOLD” from the P&IDs.