## 058-A-CAL-50002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | THIS DOCUMENT IS A SUMMARY/REPORT AND NOT A CALCULATION. THUS THE DOCUMENT TYPE SHALL BE 'RPT' AND NOT 'CAL'. CHANGE THE DOCUMENT NUMBER AND CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A CALCULATION THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY.
2 | Cloud+ | 1 | MAK | REFINERY GAS SYSTEM
3 | Cloud+ | 1 | MAK | REFINERY GAS SYSTEM
4 | Call-out | 2 | Ali Hasan | Though the IA consumption for the Custody metering is not significant, detailed hydraulic for the existing IA header in the Microscrubbers area, as part of EPC work, shall be carried out to confirm the header adequacy.
5 | Text Box | 2 | MAK | As per the Equipment List, the following equipment not listed: 058V5818A 058V5818B 058V5819A 058V5819B 058V5820
6 | Text Box | 2 | Ali Hasan | a.Please include 058V5820 (Sweet Khuff Gas KO Drum) in the equipment list. b.Confirm that IA consumption for the pressure control valves associated with 058V5820 are included in the total IA consumption.
7 | Call-out | 2 | MAK | Sort the list by Item No.
8 | Cloud+ | 2 | MAK | Change to: 058V5801 058V5802 058V5803 058V5804 058U5801 058U5802
9 | Call-out | 2 | Ali Hasan | Type; for