## 058-A-MSD-00002-001-R11A
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | 058 - REFINERY FUEL GAS SYSTEM
2 | Call-out | 1 | MAK | 1
3 | Call-out | 1 | MAK | 2
4 | Call-out | 1 | MAK | 3
5 | Text Box | 1 | Mahdi Ali | Do not use FEED numbers
6 | Text Box | 1 | MAK | General Comment: The equipment data shall be placed in alignment with the location of the equipment as possible.
7 | Text Box | 1 | MAK | General Comments applies to all MSDs: 1. Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. 2. Always use NTS for MSD scale. 3. Always use A1 for MSD border size.
8 | Call-out | 1 | MAK | General Comments: 1. Any Unit number with less than 3 digits shall be padded with zero '0'. e.g. 058 2. Any existing equipment number with lass than 4 digits shall be padded with zero '0', e.g. 058D0034
9 | Call-out | 1 | Ahmed Bucheeri | Please clarify the basis of considering this service as LSS and not HSS though H2S content is higher than 1000 PPM
10 | Text Box | 1 | MAK | Verify the equipment nos. with the agreed equipment list.
11 | Call-out | 1 | MAK | Why the sequence number is different than the other sheets?